## Instructions
Introduction
Risk management matrices are one of the most commonly used tools for analysing a business' potential risks by
ranking risks by two separate dimensions: Probability of an adverse event occuring & Impact/Severity of outcome after the event has occurred.
Impact/Severity - The potential impact on a business or project if an adverse event occurs:
Ranked between: Insignificant (1), Minor (2), Moderate (3), Major (4) and Catastrophic (5).
Probability of an adverse event occuring:
Ranked between: Rare (1), Unlikely (2), Possible (3), Likely (4) and Almost Certain (5)
Risk Rating/Outcome - measured between Low, Moderate, High & Extreme or colour coded (RAG Rated): Green, Yellow, Amber & Red
Low/Green - Risk Accepted. No action needs to be taken
Moderate/Yellow - Risk identified. To be monitored and action taken if/as required
High/Amber - Potential for an incident to occur. Action needs to be taken and additional control measures identified
Extreme/Red - Unnaceptable Risk. Immediate action to be taken to reduce Risk Levels
Likelihood
| Consequence | 1 | 2 | 3 | 4 | 5
|  | Rare | Unlikely | Possible | Likely | Almost certain
| 5 Catastrophic | 5 | 10 | 15 | 20 | 25
| 4 Major | 4 | 8 | 12 | 16 | 20
| 3 Moderate | 3 | 6 | 9 | 12 | 15
| 2 Minor | 2 | 4 | 6 | 8 | 10
| 1 Negligible | 1 | 2 | 3 | 4 | 5
Completing Risk Register (Sheet Two)
Column B: Insert details of current control measures in place
Column C: Taking the information from the above Matrix and using the drop down box at the top of Column C, select: Rare, Unlikely, Possible, Likely or Almost Certain
Column D: Taking the information from the above Matrix and using the drop down box at the top of Column D, select: Negligible, Minor, Moderate, Major or Catastrophic
Column E: Taking the information from the above Matrix and using the drop down box at the top of Column E, select: Green, Yellow, Amber or Red
Column F: Insert details of additional control measures to be put in place to reduce RAG rating from Red to Amber or Yello, or Amber to Yellow or Green
Column G: After identifying additional control measures, use the drop down box at the top of Column G to select: Green, Amber or Red

## Risk ID
| 1 | 2 | 3 | 4 | 5
Domains | Negligible | Minor | Moderate | Major | Catastrophic
Impact on the safety of patients, staff or public (physical/psychological harm) | Minimal injury requiring no/minimal intervention or treatment | Minor injury or illness, requiring minor intervention | Moderate injury requiring professional intervention | Major injury leading to long- term incapacity/disability | Incident leading to death
| No time off work | Requiring time off work for <3 days | Requiring time off work for 4–14 days | Requiring time off work for | Multiple permanent injuries or irreversible health effects
|  | Increase in length of hospital stay by 1–3 days | Increase in length of hospital stay by 4–15 days | >14 days
|  |  | RIDDOR/agency reportable incident | Increase in length of hospital stay by >15 days
|  |  | An event which impacts on a small number of patients | Mismanagement of patient care with long-term effects
Quality/complaints/audit | Peripheral element of treatment or service sub- optimal | Overall treatment or service suboptimal | Treatment or service has significantly reduced effectiveness | Non-compliance with national standards with significant risk | Totally unacceptable level or quality of treatment/service
| Informal complaint/inquiry | Formal complaint (stage 1) Local resolution | Formal complaint (stage 2) complaint | to patients if unresolved
|  | Single failure to meet internal standards | Local resolution (with potential to go to independent review) | Multiple complaints/ independent review | Inquest/ombudsman inquiry
|  | Minor implications for patient safety if unresolved | Repeated failure to meet internal standards | Low performance rating Critical report | Gross failure to meet national standards
|  | Reduced performance rating if unresolved | Major patient safety implications if findings are not acted on
Human resources/ organisational development/staffing/ competence | Short-term low staffing level that temporarily reduces service quality (< 1 day) | Low staffing level that reduces the service quality | Late delivery of key objective/ service due to lack of staff | Uncertain delivery of key objective/service due to lack of staff | Non-delivery of key objective/service due to lack of staff
|  |  | Unsafe staffing level or competence (>1 day) | Unsafe staffing level or competence (>5 days) | Ongoing unsafe staffing levels or competence
|  |  | Low staff morale | Loss of key staff | Loss of several key staff
|  |  | Poor staff attendance for mandatory/key training | Very low staff morale | No staff attending mandatory training /key training on an
|  |  |  | No staff attending mandatory/ | ongoing basis
key training
Statutory duty/ inspections | No or minimal impact or breech of guidance/ statutory duty | Breech of statutory legislation | Single breech in statutory duty | Enforcement action | Multiple breeches in statutory duty
|  | Reduced performance rating if unresolved | Challenging external recommendations/ improvement notice | Multiple breeches in statutory duty | Prosecution
|  |  |  | Improvement notices Low performance rating Critical report | Complete systems change required
Zero performance rating Severely critical report
Adverse publicity/ reputation | Rumours | Local media coverage | Local media coverage | National media coverage with <3 days service well below reasonable public expectation | National media coverage with >3 days service
| Potential for public concern | – short-term reduction in public confidence | – long-term reduction in public confidence |  | well below reasonable public expectation. MP concerned (questions in the House)
|  | Elements of public expectation not being met |  |  | Total loss of public confidence
Business objectives/ projects | Insignificant cost increase/ schedule slippage | <5 per cent over project budget | 5–10 per cent over project budget | Non-compliance with national 10–25 per cent over project budget | Incident leading
|  | Schedule slippage | Schedule slippage | Schedule slippage | >25 per cent over project budget
|  |  |  | Key objectives not met | Schedule slippage
Key objectives not met
Finance including claims | Small loss | Loss of 0.1–0.25 per cent of budget | Loss of 0.25–0.5 per cent of budget | Uncertain delivery of key objective/Loss of 0.5–1.0 per cent of budget | Non-delivery of key objective/ Loss of >1 per cent of budget
| Risk of claim remote | Claim less than £10,000 | Claim(s) between £10,000 and £100,000 | Claim(s) between | Failure to meet specification/ slippage
|  |  |  | £100,000 and £1 million | Loss of contract / payment by results
|  |  |  | Purchasers failing to pay on time | Claim(s) >£1 million
Service/business interruption | Loss/interruption of >1 hour | Loss/interruption of >8 hours | Loss/interruption of >1 day | Loss/interruption of >1 week | Permanent loss of service or facility
Environmental impact | Minimal or no impact on the environment | Minor impact on environment | Moderate impact on environment | Major impact on environment | Catastrophic impact on environment

## Risk Register
BWF Woodworking Business Risk Register
Risk | Current controls in place | Exposure/Likelihood/ Probability (1-5) | Consequence/ Impact/Severity (1-5) | Risk Rating | Additional Controls Required | Revised Risk Rating | Responsible person | BWF Toolkit | BWF Toolkit Plus | Notes
Procurement |  |  |  | 0
Timber illegal |  |  |  | 0 |  |  |  | BWF Responsible Sourcing Toolkit (RPP)/BWF Guide to EUTR |  | EUTR can lead to criminal prosecution
Timber unsustainable |  |  |  | 0 |  |  |  | BWF Aggregate Chain of Custody Service |  | Reputational risk/opportunity
Timber and Ancillaries - Moisture problems at gate |  |  |  | 0 |  |  |  | BWF Guidance on Moisture Management |  | Vital check by trained staff
Timber and Ancillaries - Properties of components |  |  |  | 0 |  |  |  | Helpline, Guidance notes Goods inwards checks in FPC |  | Clear specification and trained staff checking (can you trust information)
Timber and Ancillaries - Compatibility |  |  |  | 0 |  |  |  | Helpline, Guidance notes Goods inwards checks in FPC |  | Will any product invalidate your test/certification details
Wrong product or component being supplied |  |  |  | 0 |  |  |  | BWF Template FPC |  | How are orders checked, who signs them off?
Price volatility/increases timber |  |  |  | 0 |  |  |  | Wood Price indices (available externally) |  | How long are price agreements in place for, how long is your supplier or your business hedged for?
Price volatility/increases on other components |  |  |  | 0 |  |  |  | Use ONS/Industry data |  | How long are price agreements in place for, how long is your supplier or your business hedged for?
Resilience of supply |  |  |  | 0 |  |  |  | BWF Associates Network (and online exhibition) |  | Have you got a Plan B, is all of your supply with one company, how stable are they
Late delivery component 1 |  |  |  | 0 |  |  |  | Measure performance through Factory Production Control System |  | May be a need to consider each of your supplier relationships seperately
Late delivery component 2 |  |  |  | 0
Late delivery component 3 |  |  |  | 0
Trading terms - days credit, account limits & how effects cash flow |  |  |  | 0 | [5 empty] | Are these clear, are you aware, do you negotiate and do you cascade
Dependency on associated trades e.g. wood turners, veneering, carvers |  |  |  | 0 |  |  |  | BWF Associates Network (and online exhibition) |  | Is their suitable caveates and are any penalties cascaded?
Inflation - time between quoting for contract & winning work |  |  |  | 0 |  |  |  | BWF Standard Terms of Business/Template Contracts |  | See BWF Guidance, but ensure quotes are only valid for the period you are confident inflation will not impact your business
Operational
Inefficient (relative to market) |  |  |  | 0 |  |  |  | BWF Template FPC / Lean Guidance
Process / specification drift |  |  |  | 0 |  |  |  | BWF Template FPC / Lean Guidance
Machine failure |  |  |  | 0 |  |  |  | BWF Membership Network |  | Maintenance contract, workaround, support network
H&S Management Systems fail |  |  |  | 0 |  |  |  | BWF H&S Resources
H&S accident - disaster planning and strategy |  |  |  | 0 |  |  |  | BWF H&S Helpline / Legal advice
Timber moisture movement in factory |  |  |  | 0 |  |  |  | BWF Template FPC |  | How do you measure and track through the factory/storeage area - do you keep a log?
Workforce retention, skill and knowledge |  |  |  | 0 |  |  |  | BWF CPD / WIT Forum |  | Training plans, job descriptions/role mapping (RACI model?)
Technical systems failure |  |  |  | 0 |  |  |  | BWF Helpline
Corporate amnesia |  |  |  | 0 |  |  |  | BWF Newsletter / Meetings / Network |  | How do you record / analyse and avoid repetition of mistakes (ISO 9001 is helpful here)
Business continuity plan |  |  |  | 0 |  |  |  | BWF Template Document |  | This may be a requirement of your insurance
Business plan and strategic plan |  |  |  | 0 |  |  |  | Guide to Running a Joinery Business |  | Does the organisation have clear direction and a plan
Customer Management |  |  |  | 0 |  |  |  | BWF Guidance and Helplines |  | Systems in place and people trained?
Order slippage |  |  |  | 0 | [5 empty] | Avoidance priority # 1, Communication priority # 2
Change management |  |  |  | 0 |  |  |  | Guide to Running a Joinery Business |  | Is the organisation evolving and are people coming with you?
0
Business Compliance
Company Law, fulfilling responsibilities as a company Director |  |  |  | 0 |  |  |  | BWF Guidance and Legal Helpline
Employment contracts |  |  |  | 0 |  |  |  | BWF Template and Legal Helpline
Financial reporting requirements |  |  |  | 0 |  |  |  | BWF Financial Helpline |  | A second opinion is often worth getting
Insurance |  |  |  | 0 |  |  |  | BWF Associates Network (and online exhibition) |  |  | 30 | 6000
H&S Equipment (PPE, Dust Extraction etc.) |  |  |  | 0 |  |  |  | H&S Hero Guidance
Treatments/coatings - VOCs and long term impact |  |  |  | 0 |  |  |  | BWF Website/COSHH Asessment guidance
Sales contract (Terms & conditions) |  |  |  | 0 |  |  |  | BWF Template Documentation |  | Clear contractual terms are essential and limit damage from disputes/complaints
IT and Information
Information Security |  |  |  | 0 |  |  |  | BWF Business Continuity Guidance
Data back-up |  |  |  | 0
Cyber Security (servers and mobile devices) |  |  |  | 0
0
Product Compliance
Breach Construction Products Regulations |  |  |  | 0 |  |  |  | BWF CE Marking Toolkit |  | If you are not CE Marking, trading standards may not catch you but if you end up in a dispute, failure to provide paperwork puts you over a barrel
Breach Building Regulations |  |  |  | 0 |  |  |  | BWF Guidance and Helplines |  | Part Q is the latest, but a clear understanding of compliance with building regs is critical (remember regional variances)
Breach Conservation or Heritage Laws |  |  |  | 0 |  |  |  | BWF Guidance and Helplines |  | Have you offered advice? Do you know where the product is going?
Clear understanding specification |  |  |  | 0 |  |  |  | BWF Guidance and Helplines |  | Have you even seen it, are the customer requirements clear and documented?
Storage issues on site |  |  |  | 0 |  |  |  | BWF Guidance and Helplines |  | To avoid claims against you, have you checked e.g. moisture and got sign off at delivery, have you included clear instruction/offered training?
Installation problems |  |  |  | 0 |  |  |  | BWF Guidance and Helplines |  | Have you included clear instruction/offered training?
Installer competence |  |  |  | 0 |  |  |  | BWF Guidance and Helplines |  | If you are responsible for installation, how do you assess competence?
Claim on guarantee |  |  |  | 0 |  |  |  | BWF Guidance and Helplines |  | Are you cascading guarantees from your suppliers accurately, do they cover work to replace?
Component failure (e.g. Coating) |  |  |  | 0 |  |  |  | BWF Guidance and Helplines/Manage through FPC system
Product underperformance/customer complaint |  |  |  | 0 |  |  |  | BWF Guidance and Legal Helpline, BWF Expert Witness Services, BWF Dispute Resolution Services |  | Wedlake Bell - Doomsday scenario and product recalls
Critical Failure |  |  |  | 0 |  |  |  | BWF Guidance and Legal Helpline, BWF Expert Witness Services, BWF Insurance Partners |  | Is your role in product design clear, do you have PI cover, are there any product recall procedures in place
0
Product
Failure to innovate |  |  |  | 0 |  |  |  | BWF Technical Meetings and Newsletter |  | Don't get left behind!
Technical/Intellectual Knowledge |  |  |  | 0 |  |  |  | BWF Technical Meetings and Newsletter |  | How do you keep up to date with developments, new thinking and product improvement ideas
0
Building Management
Electrical Safety |  |  |  | 0 |  |  |  | BWF H&S Audit
Fire safety |  |  |  | 0 |  |  |  | BWF H&S Audit
Facilities maintenance and upkeep |  |  |  | 0 |  |  |  | BWF H&S Audit
Building Security |  |  |  | 0 |  |  |  | BWF H&S Audit
Insurance (building) |  |  |  | 0 |  |  |  | BWF Code of Conduct Compliance/Associate member services
H&S |  |  |  | 0 |  |  |  | BWF H&S Audit
Interest rates (linked to financial) |  |  |  | 0
Rent - lease agreements |  |  |  | 0 |  |  |  | BWF Helpline advice when negotiating rental
Business Rates |  |  |  | 0 |  |  |  | BWF Guidance on rate negotiation
0
People
Up to the job |  |  |  | 0 |  |  |  | WIT Forum/BWF CPD
Turnover |  |  |  | 0 |  |  |  | BWF Helplines and guidance on workforce engagement
Sickness |  |  |  | 0 |  |  |  | BWF Employee Handbook/ill health advice and procedures
Morale |  |  |  | 0 |  |  |  | BWF Employee Handbook
Succession planning (over-reliance) |  |  |  | 0 |  |  |  | BWF can provide some support and training resources can help to induct new people and provide advice and support through difficult times |  | Who are the critical people in your business, what options do you have to cover them for prolonged sickness or departure
Training, knowledge and skills |  |  |  | 0 |  |  |  | WIT Forum, BWF CPD, BWF E-learning academy
Resignation / Grievance |  |  |  | 0 |  |  |  | BWF Legal Helpline |  | Rash decisions can be costly
Underperforming Staff |  |  |  | 0 |  |  |  | BWF Legal Helpline / Employment Advice/BWF CPD
Downsizing / Restructuring / Redundancies |  |  |  | 0 |  |  |  | BWF Legal Helpline / Employment Advice
Recruitment & retention |  |  |  | 0 |  |  |  | BWF Template Contracts / Helplines/BWF CPD
Attracting top talent |  |  |  | 0 |  |  |  | WIT Forum / Wow I Made That / BWF Centres of Excellence/Just Joinery LinkedIn
0
Financial/Contractual
Breach T&Cs |  |  |  | 0 |  |  |  | BWF Template Documents
Customer complaint (management thereof) |  |  |  | 0 |  |  |  | BWF Complaints Management Template
Alternative Dispute Resolution option |  |  |  | 0 |  |  |  | BWF Disputes Resolution Services |  | Remember consumers must now be offered ADR
Project delays |  |  |  | 0 |  |  |  | BWF Legal Helpline to review contractors T&C's
Project failure (cancellation or looking for blame) |  |  |  | 0 |  |  |  | BWF Legal Helpline to review contractors T&C's
Late payment |  |  |  | 0 |  |  |  | BWF Fair Payment Campaign and Credit Management Guidance and Partnership
Customer goes bust |  |  |  | 0 |  |  |  | BWF Guide to Credit Control
Retentions |  |  |  | 0 |  |  |  | BWF Fair Payment Campaign and Credit Management Guidance and Partnership
Managing cash flow - forecasting & daily |  |  |  | 0 |  |  |  | BWF Guide to Running a Joinery Business
Managing Bank, HMRC |  |  |  | 0 |  |  |  | BWF Guide to Running a Joinery Business
Liquidity - how fast can cash be generated |  |  |  | 0 |  |  |  | BWF Guide to Running a Joinery Business
Profit & loss |  |  |  | 0 |  |  |  | BWF Guide to Running a Joinery Business
Breakeven analysis - knowing costs & margins. Get price right! |  |  |  | 0 |  |  |  | BWF Guide to Running a Joinery Business
0
Winning work
Marketing |  |  |  | 0 |  |  |  | BWF Marketing Toolkit
Managing interest |  |  |  | 0 |  |  |  | BWF Marketing Toolkit
Accurate and strategic quotations/estimates |  |  |  | 0 |  |  |  | BWF Estimation Training
Lead-time |  |  |  | 0
Availability |  |  |  | 0
Promotional literature - getting the right message across |  |  |  | 0 |  |  |  | BWF Marketing Toolkit
Web site & social media |  |  |  | 0 |  |  |  | BWF Marketing Toolkit
Building business relationships & customer relationship management (CRM) |  |  |  | 0 |  |  |  | BWF Marketing Toolkit
Large Account Risk |  |  |  | 0 |  |  |  | BWF E-leaning/Analyse % turnover between clients
0
External risks
Force Majeure - Infrastructure and logistic routes |  |  |  | 0 |  |  |  | BWF Standard Terms of Business/Template Contracts/Insurance cover level
Competition - price undercutting |  |  |  | 0 |  |  |  | BWF Marketing Toolkit/SWOT Analysis of USPs
Reputation of individual company |  |  |  | 0
Reputation of product, material and industry |  |  |  | 0 |  |  |  | BWF Campaigning & lobbying
PR/social media reputational risk - people, companies, industry, product |  |  |  | 0
Political risk (Brexit, legislation, regulation, government change) |  |  |  | 0 |  |  |  | BWF Newsletter
Supplier risk - e.g. ceased trading, product withdrawn, product failure |  |  |  | 0
Weak economies |  |  |  | 0 |  |  |  | BWF Market Reports and CPA Forecasting
Global market risk - external forces on customer opinion of timber. Greenpeace |  |  |  | 0 |  |  |  | BWF Newsletter
Merger & acquisition - competitors, supplier or own |  |  |  | 0

## Future Strategic Issues
Risk | Timing | Exposure | Impact | Responsible person | Company Preparation | BWF Activity